## Readme
Topic | Guidance
Purpose | Research strategy for an evidence-linked Objais revenue model. No financial forecast or research experiment has been executed.
Geography | Global evidence with Brazil and Europe highlighted; research Portugal and Brazil as specific countries, never presume insurance availability.
Route | Ten planned sequential stages; nine gates. A single research lead maintains event definitions and provenance.
Primary evidence | Confirm payment rights, paid event outcomes, acquisition and fulfilment costs before calibrated model outputs.
Counts | 22 data requests; 34 blank parameter records; four proposed experiments; nine baseline file identities.
Parameters | Blue value/source/period cells are blank for actual research inputs. Definitions, owners and next requests are prefilled; unknown is not zero.
Evidence status | observed, contract-supported, proxy, scenario assumption, unavailable, not applicable. Preserve a source and date for every supplied value.
Rates | Use an explicit unit: fractions between 0 and 1 for model probabilities; currencies and billing periods must be stated.
Sample limits | Proposed qualitative interviews are directional; a 60-90 day pilot does not validate annual renewals.
Model horizon | Future target: 36 monthly periods, cohorts, segment-country-channel detail, native EUR/BRL and explicit consolidated FX.
Scope | This workbook is an evidence collection plan. Actual model outputs remain a future deliverable.
Dispatch validation | The installed dispatch-spec validator reports pass for route shape. Gates have definitions; their runtime conditions are not established.
Use | Read the strategy, request P0 evidence, complete parameter sources, and apply lane-selection gate before widening fieldwork.

## Route
Stage | Task | Capability reference | Question | Inputs | Outputs | Completion criteria | Stop conditions | Planned effort
s01 | Freeze scope and evidence baseline | context-builder | What is established about product, geography and commercial assumptions? | objais-revenue-research-20261013-v1 research/revenue-strategy/baseline-manifest.json | research/revenue-model/scope.json research/revenue-model/evidence-register.csv | Import dated evidence with source ids and hashes; deduplicate URLs without discarding period differences Separate advertised, actually transacted and planned categories Define 36 monthly periods, segment-country-channel units and EUR/BRL native inputs | If existing evidence is inconsistent, record conflict and continue with a bounded scope; no invented live product or country | 0.5 research day
s02 | Establish payable events and commercial rights | task-session | Who pays, for what event, on what terms and for how long? | research/revenue-model/scope.json research/revenue-model/evidence-register.csv research/revenue-strategy/data-requests.csv | research/revenue-model/commercial-rights.csv research/revenue-model/revenue-options.json | Record contracts or written commercial terms, territory, trigger, net fee/split, refunds, exclusivity, payment delay and future rights Keep paid lead, binding commission, renewal, referral and software payments distinct Mark unavailable terms as unknown; alternative price precedents remain proxies | Without confirmed payable terms, produce a symbolic/scenario model and block any contract-calibrated base forecast Do not initiate external outreach or commercial commitments during automatic execution | 1-2 research days after terms are supplied
s03 | Define and reconcile the funnel and costs | task-session | How do observable events become paid revenue and attributable costs? | research/revenue-model/revenue-options.json research/revenue-model/commercial-rights.csv research/revenue-strategy/parameter-register.csv | research/revenue-model/metric-dictionary.json research/revenue-model/cohort-facts.csv research/revenue-model/cost-register.csv | Define session/prospect/lead/policy identifiers and conversion denominators Reconcile all available deidentified event, invoice, insurer-acceptance and cash records Separate anonymous estimates, unique consented prospects, duplicate requests and policies Assign acquisition, per-event data, specialist and support costs; separate fixed costs | Unlinked events remain unclassified rather than forcing attribution If cohort data are unavailable retain uncalibrated ranges and identify the next observable event | 1-2 research days after data are supplied
s04 | Screen segment country and channel choices | decision-gate | Which two lanes deserve primary collection research and which are desk comparators? | research/revenue-model/scope.json research/revenue-model/commercial-rights.csv research/revenue-model/cohort-facts.csv research/revenue-model/cost-register.csv | research/revenue-model/segment-selection.json | Assess existing watches/jewellery, TCG counterfactual and pets plus other current categories Hard screen for actual underwriting/distribution access before economics ranking Select at most two segment-country-channel lanes, recording rejected and deferred alternatives Use feasible contribution, evidence confidence and test cost rather than total-market size | If no lane has an accepted product/counterparty route, stop sales/premium forecasts for those lanes and preserve demand research No scored ranking made from missing private metrics | 0.5 research day; operator owns final selection
s05 | Research paid demand repeat tasks and distribution | task-session | Which completed tasks cause a repeat visit or payment and how can users be acquired? | research/revenue-model/segment-selection.json research/revenue-model/metric-dictionary.json research/revenue-strategy/experiments.json | research/revenue-model/demand-and-channel-evidence.csv research/revenue-model/experiment-designs.json | Design directional interviews and pricing/distribution probes for selected lanes Record behaviour, existing alternatives, actual payment or accepted offer evidence separately from stated interest Define meaningful D30/D60/D90 actions and per-channel paid yield Keep future human-run interviews and experiments unexecuted until separately commissioned | No unsolicited messaging, paid campaign, live quote, app experiment or user recruitment in this strategy task Stop weak feature hypotheses if users already solve the task and no differentiated payment/service route exists | 2-3 research days for design; human fieldwork and 60-90 day pilot separate
s06 | Verify fulfilment underwriting and service constraints | task-session | Can an intended request actually be accepted and serviced at the modeled cost? | research/revenue-model/segment-selection.json research/revenue-model/commercial-rights.csv research/revenue-model/experiment-designs.json | research/revenue-model/fulfilment-and-access.csv research/revenue-model/model-inputs.json | Obtain category-country acceptance criteria, limits, minimum premiums, valuation evidence and update/claims rights Confirm usable data supply and pricing rights; distinguish prototype from production access Record completion time, rejection causes and per-case specialist/support cost Every numeric parameter gets unit, denominator, period, source, status, range and owner | Unsupported country/category or future service revenue remains disabled in actual base case Public product precedent cannot become a signed Objais term | 1-2 research days after partner evidence is supplied
s07 | Build the monthly cohort revenue model | task-session | What revenue contribution and cash follow from each supported model? | research/revenue-model/model-inputs.json research/revenue-model/demand-and-channel-evidence.csv research/revenue-model/cost-register.csv | research/revenue-model/Objais Revenue Model.xlsx research/revenue-model/model-specification.md research/revenue-model/scenario-results.csv | 36 months, cohort and segment-country-channel outputs, explicit native currencies and dated FX for consolidated EUR view One-off leads are baseline; commissions, renewal, referrals and software activate only with evidence or explicit scenario flag Separate recognized revenue, invoicing and cash; prevent duplicate monetization of the same event Show downside/base/upside, causal sensitivities, break-even yield/CAC and payback | Unknown input is not zero; do not issue calibrated results from blank critical terms Do not multiply global TAM by arbitrary capture rate | 2 research days after critical inputs are available
s08 | Validate accounting identities cohorts and uncertainty | task-session | Does the model reconcile and survive credible failures? | research/revenue-model/Objais Revenue Model.xlsx research/revenue-model/model-inputs.json research/revenue-model/cohort-facts.csv research/revenue-model/model-specification.md | research/revenue-model/validation-report.json research/revenue-model/sensitivity-and-residue.csv | Test zero acquisition, zero conversion, no renewal rights, cancellations, refunds, duplicates, cost scaling, FX and payment delay Reconcile eligible historical months with observed invoices/cash and explain residuals Avoid inferring annual renewals from 60-90 day engagement Repair at most three model defects per validation cycle; unresolved errors stop reliable forecast release | Invalid cash/policy balances or unexplained double counting block decision-ready release Short cohorts permit provisional scenarios, not validated annual LTV | 1 research day; bounded repair loop
s09 | Choose a revenue architecture and next experiment | decision-gate | Which architecture should be tested retained or rejected and what information would change the answer? | research/revenue-model/validation-report.json research/revenue-model/scenario-results.csv research/revenue-model/sensitivity-and-residue.csv research/revenue-model/segment-selection.json | research/revenue-model/commercial-decision.json | Compare contribution/cash/payback, access feasibility, evidence confidence, concentration and service burden Rank missing evidence by likelihood of changing the decision and cost of obtaining it Define go, revise, defer and stop outcomes with explicit rationale No winner is mandatory when evidence is insufficient | Negative conservative contribution plus no feasible corrective test means revise/stop, not a growth recommendation Economic selection is a management decision, not statutory or investment authority | 0.5 research day; operator owns choice
s10 | Deliver the model evidence and execution handoff | invoke | Can another researcher reproduce the conclusions and act on the next bounded task? | research/revenue-model/commercial-decision.json research/revenue-model/validation-report.json research/revenue-model/Objais Revenue Model.xlsx research/revenue-model/sensitivity-and-residue.csv | research/revenue-model/handoff.json research/revenue-model/Revenue Model Decision Memo.md | Deliver source-linked workbook, formulas, assumptions, actual vs scenario labels, decision memo and next data request Record forecast calibration status and remaining owners/dependencies Deliver a bounded next task with verification evidence; no automatic rollout or external commitment | Critical model defect or unsupported commercial term prevents a decision-ready label Route completion does not create promotion or publication authority | 0.5 research day

## Data Requests
request_id | priority | area | input | requested_evidence | owner | preferred_source | definition | model_implication
R01 | P0 | Commercial | Payment basis | Actual insurer/intermediary terms per category/country: accepted lead, binding commission or both | Commercial owner | Executed agreement or written commercial confirmation | Payable event and mutually exclusive/incremental rules | Revenue definition blocks calibrated base
R02 | P0 | Commercial | Net fee and split | Net accepted-lead fee or commission rate, partner revenue share, taxes/pass-through treatment | Commercial/finance owner | Agreement, rate card and matching invoice | Native currency, valid dates and territory | Cannot infer from gross premium
R03 | P0 | Commercial | Future fees | Renewal, endorsement, service/referral or recurring fees and retention rights | Commercial owner | Agreement and payment history if any | Explicit yes/no/unknown per revenue stream | Zero only if confirmed absent or explicit lead-only scenario
R04 | P0 | Commercial | Rejections and reversals | Acceptance rules, duplicates, exclusivity, refunds, cancellations and clawbacks | Commercial/operations owner | Contract and actual accepted/rejected records | Reason code and linked payable event | Prevents overstated paid yield
R05 | P0 | Commercial | Timing | Invoice trigger, settlement delays and overdue balances | Finance owner | Invoices, receipts and accounts-receivable ageing | Month invoiced and paid | Revenue is separate from cash
R06 | P0 | Funnel | Activity and attribution | All available monthly cohorts preferably 6-12 months: category, country, channel and observed event counts | Product/data owner | Deidentified export with metric definitions | Estimate session, prospect, request, lead, policy identifiers | No forced identity link for anonymous estimates
R07 | P0 | Funnel | Paid outcomes | Accepted paid leads, quotes, bound policies, cancellations and invoice links | Operations/finance owner | Counterparty acceptance and matching finance records | Dates, original cohort and duplicates | Advertised categories are not transactions
R08 | P0 | Costs | Acquisition cost | Channel spend, attributable acquisition counts, partner payouts, campaign definitions | Growth/finance owner | Invoices and attributable cohorts | Paid-channel and blended cost; acquisition unit | No platform cost-per-click as CAC
R09 | P0 | Costs | Variable service cost | Image/data usage, licensing, support, specialist time, policy servicing and referrals | Product/operations/finance owner | Bills, usage and time samples | Driver and event denominator | Returns can increase cost without revenue
R10 | P0 | Feasibility | Accepted products | Insurer/intermediary, country/category acceptance, valuation requirements and minimum premiums | Licensed insurance counterpart | Product wording, mandate and acceptance criteria | Source version, coverage and current availability | Unsupported base-case lanes remain disabled
R11 | P1 | Retention | Useful return actions | Records added, sold items removed, accepted updates, service requests and claims tasks by original cohort | Product/data owner | Observed events with eligibility windows | D30/D60/D90 meaningful actions; not notification opens | Engagement cannot proxy renewal revenue
R12 | P1 | Retention | Policy continuation | Renewal due dates, matured renewal cohorts, observed renewed/cancelled policies and actual fees | Operations/finance owner | Policy and payment history | Original policy cohort and 12-month maturity | No annual retention inferred from a 90-day pilot
R13 | P1 | Demand | Collection and purchase behaviour | Job to be done, owner/delegate, current tools, collection bands and actual acquisition events | Research lead with separately commissioned fieldwork | Directional interviews and task observation | Selected adult participants, not population sample | Identify differentiated repeat tasks
R14 | P1 | Demand | Payment evidence | Actual paid outcomes or clearly defined priced offers for a completed task | Research lead / commercial owner | Confirmed payment or offer/acceptance/refusal | Observed, conditional commitment or stated interest distinguished | Interest is not paid conversion
R15 | P1 | Distribution | Partner route | Actual retailer/vet/marina/marketplace/broker access and proposed commercial terms | Commercial owner | Channel agreement or bounded experiment receipt | Eligible users, completion and net paid yield | Audience claims do not establish affordable acquisition
R16 | P1 | Data | Reference rights | Category-specific valuation feeds, local price relevance, licence limits and update costs | Product/data owner | Supplier terms and costs | Coverage, variant accuracy and permitted reuse | Public API advertising is not a licence
R17 | P1 | Servicing | Operational access | Document acceptance, quote/policy updates, reimbursements and servicing integrations | Operations and insurer owner | Technical/service agreement and sample accepted submission | Who owns work, timing and cost | A dashboard change does not amend insurance
R18 | P1 | Economics | Customer overlap | Observed cross-category requests and paid outcomes with stable permitted linking | Product/data owner | Deidentified cohort data | Same acquired user with deduplicated payable events | Do not count one user as several independent acquisitions
R19 | P2 | Forecast | Capacity and fixed cost | Staff, tools, partner limits, specialist throughput and overhead | Finance/operations owner | Budget and capacity data | Monthly fixed and capacity-driven costs | Contribution is not operating profit
R20 | P2 | Forecast | Currency and management reporting | Reporting currency, dated FX, forecast start month and finance revenue/cash convention | Finance owner | Approved management-model convention | Native BRL/EUR plus explicit consolidated FX | No mixed-currency totals
R21 | P2 | Risk | Concentration | Paid revenue and eligible capacity by insurer and channel | Finance/operations owner | Monthly counterparty data | Share, contracts and replaceability | Model loss of a major counterparty
R22 | P2 | Software | Paid software terms | B2C/B2B service scope, per-account/seat/task prices, billing period and renewals | Commercial/product owner | Offer tests or executed terms | Activate scenario only until paid evidence exists | Free-user growth does not equal subscriptions

## Parameters
parameter_id | parameter | unit | grain | definition | low | base | high | evidence_status | source_ref | period | owner | next_request
P01 | Acquired units | unique prospects or documented sessions | segment-country-channel-month | Observed acquisition denominator; identity limitations explicit |  |  |  | unavailable |  |  | Product/data owner | R06
P02 | Cost per acquired unit | native currency per acquired unit | channel-month | Spend over eligible acquisitions; blended/paid distinguished |  |  |  | unavailable |  |  | Growth/finance owner | R08
P03 | Qualified-request rate | fraction | acquisition cohort | Qualified requests divided by acquired units |  |  |  | unavailable |  |  | Operations/finance owner | R07
P04 | Paid acceptance conditional on qualified request | fraction | lead cohort | Paid accepted leads divided by qualified requests |  |  |  | unavailable |  |  | Operations/finance owner | R07
P05 | Net fee per accepted paid lead | native currency per paid lead | contract/category/country | After contractual partner split; define before/after refunds |  |  |  | unavailable |  |  | Commercial/finance owner | R02
P06 | Lead reversal fraction | fraction | accepted-lead cohort | Reversed payable leads divided by accepted paid leads |  |  |  | unavailable |  |  | Commercial/operations owner | R04
P07 | Quote to policy binding fraction | fraction | eligible quote cohort | Bound policies divided by eligible insurer quotes |  |  |  | unavailable |  |  | Operations/finance owner | R07
P08 | Average written premium per bound policy | native currency per policy | policy cohort | Gross written premium distinct from broker revenue |  |  |  | unavailable |  |  | Operations/finance owner | R07
P09 | New policy commission rate | fraction of eligible premium | commercial agreement | Base and payable trigger require confirmation |  |  |  | unavailable |  |  | Commercial/finance owner | R02
P10 | Objais retained commission share | fraction | partner agreement | Do not subtract partner split again from already-net rate |  |  |  | unavailable |  |  | Commercial/finance owner | R02
P11 | Cancellation and commission clawbacks | native currency or fraction with explicit unit | policy cohort | Reason, due dates and cash reversal links |  |  |  | unavailable |  |  | Commercial/operations owner | R04
P12 | Policies due for renewal | policies | policy origination month | Mature due cohorts only |  |  |  | unavailable |  |  | Operations/finance owner | R12
P13 | Annual policy renewal fraction | fraction | mature policy cohort | Unknown if no annual cohort has matured |  |  |  | unavailable |  |  | Operations/finance owner | R12
P14 | Renewal net fee or commission | native currency per renewed policy OR fraction | contract | Explicit contractual eligibility and denominator |  |  |  | unavailable |  |  | Commercial owner | R03
P15 | Meaningful D30/D60/D90 retention | fraction per stated window | user cohort | Completed task among users eligible to reach window |  |  |  | unavailable |  |  | Product/data owner | R11
P16 | Paid service referral rate | fraction of eligible users/tasks | service cohort | Triggered by completed paid service, not click |  |  |  | unavailable |  |  | Research lead / commercial owner | R14; R17
P17 | Net fee per completed paid service | native currency per service | service contract | Refunds/pass-through and cost basis explicit |  |  |  | unavailable |  |  | Commercial owner | R03; R14
P18 | New paid software conversion | fraction of eligible users/accounts | software cohort | Observed price and actual paid outcome |  |  |  | unavailable |  |  | Research lead / commercial owner | R14; R22
P19 | Monthly paid software churn | fraction of beginning active paying accounts | software cohort | Cancellations/downgrades; never mix annual and monthly churn |  |  |  | unavailable |  |  | Commercial/product owner | R22
P20 | Software price and billing period | native currency per account/seat/task and period | offer/contract | Annual cash versus monthly management revenue distinguished |  |  |  | unavailable |  |  | Commercial/product owner | R22
P21 | Scan and identity cost | native currency per processed image | usage | Provider/compute usage plus failed scans |  |  |  | unavailable |  |  | Product/operations/finance owner | R09
P22 | Valuation data cost | native currency fixed/month/per record | supplier licence | Coverage and permitted usage documented |  |  |  | unavailable |  |  | Product/data owner | R16
P23 | Support and specialist cost | native currency per minute/case | observed workflow | Duration, wage/vendor rate and failed cases included |  |  |  | unavailable |  |  | Product/operations/finance owner | R09
P24 | Storage and notification cost | native currency per record/month/event | usage | Scale with active holdings/events not new acquisitions only |  |  |  | unavailable |  |  | Product/operations/finance owner | R09
P25 | Quote and policy servicing cost | native currency per request/policy/update | workflow | Incremental burden of a recurring offer |  |  |  | unavailable |  |  | Operations and insurer owner | R17
P26 | Payment processing and bad debt | native currency/fraction of documented base | payment cohort | Invoice failures and failed collections |  |  |  | unavailable |  |  | Product/operations/finance owner | R09; R05
P27 | Settlement lag | months/days with distribution | payer | Recognized revenue/invoice/cash distinct |  |  |  | unavailable |  |  | Finance owner | R05
P28 | Fixed monthly operating cost | native currency per month | operating plan | Staff, tools and overhead outside contribution |  |  |  | unavailable |  |  | Finance/operations owner | R19
P29 | Accepted submission capacity | cases per specialist/partner-month | operational counterparty | Do not grow sales beyond evidenced/assumed capacity |  |  |  | unavailable |  |  | Finance/operations owner | R19
P30 | Country-category availability | confirmed/unsupported/unknown | jurisdiction and current product | Hard inclusion condition for supported base lane |  |  |  | unavailable |  |  | Licensed insurance counterpart | R10
P31 | Cross-category paid overlap | linked unique users/events | acquisition cohort | Deduplicate acquisition and payable triggers |  |  |  | unavailable |  |  | Product/data owner | R18
P32 | Dated FX rate | EUR per BRL or explicitly stated direction | month | Native figures remain available; consolidation reproducible |  |  |  | unavailable |  |  | Finance owner | R20
P33 | Counterparty concentration | share of net revenue or capacity | payer/channel/month | Shock both revenue and replacement cost |  |  |  | unavailable |  |  | Finance/operations owner | R21
P34 | Retention cost uplift | native currency per returning user/event | user cohort | Repeat use increases cost even if future fee equals zero |  |  |  | unavailable |  |  | Product/operations/finance owner | R09; R11

## Revenue Options
Architecture | Payable base | Revenue definition | Activation rule | Evidence | Duplicate or claim risk
One-off leads | Accepted payable leads | Net fee less documented reversals | Keep as initial working baseline | Written payer terms and accepted/paid event evidence | No renewal income without rights
Binding commissions | Eligible bound premium | Rate times retained share less clawbacks | Alternative or documented incremental contract | Executed/written commission terms plus policy history | Avoid counting lead fee and full commission for same event by default
Renewal / ongoing fees | Eligible renewed/serviced policy cohort | Contract net fee or commission basis | Only with rights or explicit hypothesis scenario | Terms plus mature cohorts and service cost | Product return visits are not policy renewals
Specialist referrals | Completed payable service | Net referral fee less reversals | Activate with service terms and actual paid outcomes | Provider fee terms, completion and invoice links | Clicks are not earned fees
Paid software / documentation | Billable account, seat, task or portfolio | Price by service and billing period | Demand hypothesis until paid evidence | Priced offer/payment, delivery cost and continuation | Competitor price cannot establish Objais willingness to pay

## Experiments
experiment_id | purpose | method | sample | outcomes | limits | execution
E01 | Identify a repeated task and its current alternative | Directional task interviews and record walkthroughs | Proposed 24 adult owners split 12 per selected lane, plus 6 relevant counterparties; adjust recruitment to selected lane and saturation | Recent actual actions Owner versus delegate Current alternative Accepted record/service gap | Not a representative survey or conversion-rate estimate | Designed only; separately commissioned human fieldwork
E02 | Test whether a concrete completed task commands payment | Present defined task, deliverable, price, service terms and free alternatives; classify payment/conditional commitment/stated interest separately | Eligible owners in selected lane; size determined by target precision and traffic | Actual payment or priced offer outcome Reason to refuse Service cost | Price ranges are hypotheses until supported; no automatic charging or published offer | Designed only
E03 | Measure channel yield and acceptance | Attribute eligible acquisitions through an available partner channel and follow requests through paid acceptance or binding | All eligible events in a predeclared bounded period; precision sized by observed conversion | Qualified yield Paid acceptance Net fee Acquisition and fulfilment cost Payment delay | Partner existence and participation must be confirmed; no extrapolation from audience totals | Designed only
E04 | Measure useful repeat work and its economics | Track a separately authorised 60-90 day cohort, recording meaningful records/service/accepted update events and costs | Selected-lane consenting cohort with D30/D60/D90 eligibility windows | Useful return action Paid subsequent event Cost per returning user Free repeat activity without revenue | Does not validate annual policy renewal or annual software retention | Designed only

## Gates
Gate | Kind | Owner | Condition | Failure action | Stage
g01-scope | quality | research lead | Every lane has category, country, channel, status and dated baseline evidence; planned categories are separate. | flag | s01
g02-commercial-rights | quality | Objais commercial owner supplies terms; research lead checks | A payable trigger and net remuneration are evidenced for calibrated base revenue; unknown rights produce a symbolic/scenario branch. | defer | s02
g03-measurement | validation | research lead with Objais data/finance owner | Denominators, duplicate handling and cost attribution reconcile to observable events; assumptions cannot become measured metrics. | flag | s03
g04-selection | decision | operator | At most two lanes selected against actual access, potential contribution, evidence confidence and test cost. | reroute | s04
g05-fieldwork-scope | policy | operator | This task creates designs only; external interviews, experiments and spending need a separate concrete task and direct authorization before execution. | defer | s05
g06-feasibility | quality | research lead; authorised counterparties own actual terms | Supported base-case lanes have accepted categories/territories, usable reference data and documented service scope; unsupported offers remain hypotheses. | defer | s06
g07-model | validation | research lead with finance reviewer | Arithmetic, policy balances, recurring-fee rights, duplicate prevention, cash timing and provenance checks pass; projection labels match evidence maturity. | block | s08
g08-decision | decision | operator | Proceed/revise/defer/stop rationale and the next highest-value information request are explicit; no forced expansion choice. | defer | s09
g09-promotion | promotion_guardrail | owning capability and operator | This route produces task-local evidence and model artifacts only; canonical inventory, ontology, glossary, sigil or spell changes require their own owner process. | block | all

## Model Checks
Check | Subject | Expected evidence | Failure interpretation
V01 | Zero acquisition | No new acquired cohort; existing payable, renewal, service and receivable cohorts still follow their terms | Any phantom earned revenue blocks model release
V02 | Zero paid acceptance | No newly payable fees from the affected cohort; prior earned fees and other streams follow their own events | Free requests cannot become paid leads
V03 | No future rights | No renewal or ongoing revenue under a lead-only contract | Scenario assertion never establishes rights
V04 | Duplicates | Same payable event handled once unless incremental terms explicitly permit another fee | Reconcile unique event identifiers
V05 | Cancellation and refunds | Policy and fee reversals match contract and period | Check gross/net revenue and cash reversal
V06 | Policy balances | Beginning active plus newly bound minus cancelled and non-renewed expired equals ending active; renewals extend terms rather than add policies | Separate due cohorts and renewal counts
V07 | Software balances | Beginning paying accounts plus new minus churn equals ending; units and billing periods consistent | Do not apply annual churn monthly
V08 | Cost scaling | Scans, records, support and servicing scale with true drivers including free/failed activity | Check separate per-event and fixed costs
V09 | Currency and time | Native figures and FX direction reconcile; flow and stock measures remain distinct | No mixed-currency addition
V10 | Cash and revenue | Opening receivables plus invoiced less receipts/reversals equals closing receivables under finance convention | Cash delay changes cash, not fee rights
V11 | Historical reconciliation | Available observations match operational/finance records with explained residuals | Short history gives provisional calibration only
V12 | Retention maturity | D30/D60/D90 users eligible for window; annual renewals use mature due policy cohorts | No annual LTV claim from 90-day activity
V13 | Capacity and concentration | Growth respects capacity; payer/channel failure shock modeled | No unsupported production access
V14 | Input provenance | Each critical numeric input has source, period, unit, denominator and status | Blank critical input prevents calibrated base
V15 | Scenario consistency | Correlated optimistic assumptions are not all multiplied without a coherent story | Confidence separate from attractiveness

## Baseline
ref | byte_length | sha256 | role
Objais Research Report.md | 35891 | bbecd0bcee59201a1cd154359622d36f2e9d67ca9b53d9df4e92c58bb213522e | Existing company/market evidence; not company financial input
Objais Current Markets Research.md | 38270 | daff1d184741e9f979d7cdfd718487c4c3ae92171d38dad0cdc68e3a69f8fb2d | Existing company/market evidence; not company financial input
Collectibles Market Research.md | 44928 | 34509ab59743d3d8d629bbfa856aaf504e6b72e0a3571363dc84bc98db7ab014 | Existing company/market evidence; not company financial input
Objais Current Markets Data.xlsx | 42204 | 90a243cb3466982f0fa2f4ee76eb1a4fca972b56c31fd05e0cb79453792b7e7d | Existing company/market evidence; not company financial input
Collectibles Market Data.xlsx | 40233 | 5c10df7d4e303c76b6b421f9b314f746ea7f2a811a5e9a18d9889fdcf722a970 | Existing company/market evidence; not company financial input
research/current-markets/market_data.json | 46340 | fa73f0775185301a24f6914a704e539db63d6cf82151f409047e0ac1f3b2720a | Existing company/market evidence; not company financial input
research/current-markets/sources.json | 18020 | 360ae68e4f7ff27e65da7286d708c7412592dbf48d951d4aa9ac67049095b176 | Existing company/market evidence; not company financial input
research/collectibles/market_data.json | 50485 | d45912d9f0be52d309ee3bea4e7b62843320f46bd3d98bfbab81632256861b9d | Existing company/market evidence; not company financial input
research/collectibles/sources.json | 17994 | ad839c84e508e090e346bd75456c857cb9983c8f80e452176f1ee6c87b5b81ec | Existing company/market evidence; not company financial input